## excel
/Non Project/PSP Fundamentals & Advanced/Program 2
PSP1 Project Plan Summary
Debe ingresar datos actuales de tamaÃ±o para este proyecto.
El PROBE Wizard usa la EstimaciÃ³n de TamaÃ±o de Proxy como la base para generar estimados finales para el tiempo y tamaÃ±o. Sin embargo, despuÃ©s de que corriste el Wizard por Ãºltima vez, modificaste los estimados en la plantilla de EstimaciÃ³n de Tiempo, causando que el TamaÃ±o de Proxy Estimado cambiara. Su estimado PROBE actual estÃ¡ basado en un valor antiguo de TamaÃ±o de Proxy Estimado. Para resolver este problema, debe revisar los valores en la Plantilla de EstimaciÃ³n de TamaÃ±o, y correr el Wizard de nuevo
Project Settings
Project Owner | Juan Pablo Ospino Solano
Start Date | feb 19, 2017 07:28:40 AM
Completion Date | feb 22, 2017 12:23:39 PM |  |  |  | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:23 PM el 22/02/2017
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 35.6 | #VALUE! | 32.1
Program Size
Base (B) | 260 | 300 | 300
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 0
Added (A) | 142 | #VALUE! | 284
Reused (R) | 0 | 0 | 0
Added and Modified (A+M) | 142 | #VALUE! | 284
Total Size (T) | 402 |  | 0
Total New Reusable | 246 | 0 | 0
Estimated Proxy Size (E) | 246 | 10 | 10
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.0055556 | 0.0375 | 0.040972 | 11.1%
DiseÃ±o | 0.0076389 | 0.01875 | 0.023611 | 6.4%
CodificaciÃ³n | 0.13264 | 0.15208 | 0.23611 | 64%
CompilaciÃ³n | 0.0097222 | 0.0125 | 0.01875 | 5.08%
Pruebas | 0.011111 | 0 | 0.0069444 | 1.88%
Postmortem | 0 | 0.042361 | 0.042361 | 11.5%
Total | 0.16667 | 0.26319 | 0.36875
Defects Injected
| Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0%
DiseÃ±o | 3 | 3 | 37.5%
CodificaciÃ³n | 2 | 5 | 62.5%
CompilaciÃ³n | 0 | 0 | 0%
Pruebas | 0 | 0 | 0%
Total | 5 | 8
Defects Removed
| Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0%
CodificaciÃ³n | 5 | 7 | 87.5%
CompilaciÃ³n | 0 | 1 | 12.5%
Pruebas | 0 | 0 | 0%
Total | 5 | 8
After Development | 0 | 6